## Sheet1
| Task | Sept. | Oct. | Nov. | Dec. |  |  | Jan. | Feb. | Mar. | Apr.
1 | Finalize Project Idea |  |  |  |  | Exams | Break |  |  |  |  | Exams
2 | Problem Defintion
Final version of the problem definition
3 | Conceptual Design
4 | Subsystems problem defintion
5 | Conceptual Sybsystem Designs
6 | Demonstrate “Hello, world!”
Have all parts ordered
7 | Complete class activities (individuals)
8 | I/O Demos (individuals)
9 | Testing Plans
10 | Fall Demonstartion
11 | WHMIS
12 | Meetings with Super visor
13 | Development of Communication module
14 | Development of Pot-hole detection module
15 | Development of CAN-BUS module
16 | Development of GPS
17 | Development of Frontend and Backend
18 | FREERTOS
19 | Order PCB
20 | Solder PCB
21 | Testing : Communication module
22 | Testing : Pot-hole detection module
23 | Testing : CAN-BUS module
24 | Testing Frontend and Backend
25 | Testing : GPS Module
26 | Integration
27 | Full system test
28 | Faculty Presentation
Project Day presentation
…
Project report
Done
In progress
Not started
Behind
No work expected